{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["总表"],"read":"whole","date_system":"1900"}

{"sheet":"总表","index":0,"n_rows":12,"n_cols":5,"rows_kept":12,"merged":[[0,0,0,4],[2,1,6,1],[2,3,6,3],[7,1,9,1],[7,3,9,3],[10,0,10,3],[11,0,11,4]]}
["项目报价表"]
["序号","项目类别","项目名称","工作内容","报价金额"]
[1,"土地整治\n项目","巴中市南江县公山镇流坝村、流坝社区、梅岭村、渔坝村、长坪村土地整治项目","1.前期工作：收集整理相关资料文献，分析规划区自然资源、人口社会、经济状况、开发格局等涉及项目所需的资料；\n2.可研：编制可研报告、预算书、规划图以及项目附件资料；\n3.设计、预算：预算、项目图件等项目资料\n4.审批与批复：获取立项批复"]
[2,null,"巴中市南江县公山镇桥坝社区、桥坝村、田塝村、响水村土地整治项目"]
[3,null,"巴中市南江县公山镇甘溪村、华营村、桃红村土地整治项目"]
[4,null,"巴中市南江县公山镇金碑村、五星村、永红村土地整治项目"]
[5,null,"巴中市南江县公山镇石矿社区、石矿村、卫星村、跃进村、石光村、白鹤村土地整治项目"]
[6,"增减挂钩\n项目","公山镇桃红村、金碑村、永红村、五星村、田塝村、桥坝村、响水村城乡建设用地增减挂钩项目立项","1.前期工作：收集整理相关资料文献，分析规划区自然资源、人口社会、经济状况、开发格局等现状与问题，分析并整理；开展土地利用现状、权属、人口、复垦潜力、群众意愿（需≥95% 同意）等专项调查；\n2.资料编制：明确拆旧复垦规模、安置补偿、建新指标分配、实施时序与后期管；编制项目实施规划、土地复垦方案、资金预算、社会稳定风险评估等\n3.审查与踏勘：县级自然资源部门牵头，联合农业农村、住建、生态环境、水利等部门审查合规性；\n4.审批与批复：市级 / 省级政府下达立项批复"]
[7,null,"公山镇渔坝村、长坪村、华营村、甘溪村、流坝村、梅岭村城乡建设用地增减挂钩项目立项"]
[8,null,"公山镇白鹤村、石光村、跃进村、卫星村、石矿村城乡建设用地增减挂钩项目立项"]
["合计"]
["报价单位（盖章）：                                        联系人：                  电话：                 时间：                                     "]